## Backlog
Google UI Controls Sampler
Backlog
ID | Needs | Story | Acceptance Criteria | State | Effort | Date Started | Date Done | Test Sequence | Notes | Spec
6 | - | See a form attached to a spreadsheet | - menu command available to invoke form - form appears on top of spreadsheet - form has title at top | Ready | 1 |  |  |  |  | https://developers.google.com/apps-script/uiapp#DisplayingSpreadsheet
7 | 6 | Values entered into form, are copied into some sheet cells after a submit action |  | To Define | [5 empty] | https://developers.google.com/apps-script/uiapp#DisplayingSpreadsheet
8 | - | Examples work after sharing them to another account | - All examples that work in my gmail.com account, work in my linkedin.com account | Ready |  |  |  | 1) For each menu item in Extras Menu, invoke 2) Should see expected results | Not sure why this is happening. Maybe recopy script over?
9
10
Note: move the following section to a new sheet when it gets too large to view in the same sheet as the Backlog
DONE
4 | 1 | Can make a second control appear | - button visible to press to invoke second control to appear - pressing first button causes second control to appear | Done | .5/.5 | 2013-04-27 | 2013-04-27 | 1 - invoke from menu item "Extras" 2 - in dialog box, click "Press Me" 3 - in dialog box, see new second label text appear above first control | Found example from web search: Google I/O | https://developers.google.com/apps-script/uiapp#DisplayingSpreadsheet
5 | 3 | Can enter text and have it show up in spreadsheet cell | - text box visible - text box accepts text input - value entered in text box shows up in column A, last row + 1 | Done | 1,2 | 2013-04-27 | 2013-04-27 | 1 - invoke from menu item 2 - type text into text box 3 - clicking "Submit" makes panel go away 4 - Text shows up in column A, last occupied cell + 1 |  | https://developers.google.com/apps-script/uiapp#DisplayingSpreadsheet
3 | - | Can enter text into a UI control | - text box visible - text box accepts text input | Done | .5/.5 | 2013-04-27 | 2013-04-27 | 1 - invoke from menu item 2 - type text into text box 3 - clicking "Submit" makes panel go away | http://www.youtube.com/watch?v=5VmEPo6Rkq4 | https://developers.google.com/apps-script/uiapp#DisplayingSpreadsheet
2 | 1 | Can make interaction panel disappear | - pressing a control makes the panel disappear | Done | 1,.5 | 2013-04-27 | 2013-04-27 | 1 - invoke from Extras menu item 2 - in dialog box, click button "Press Me" 3 - see panel go away |  | https://developers.google.com/apps-script/uiapp#DisplayingSpreadsheet
1 | - | See a interaction panel | - Invoked from menu item - See basic panel in front of spreadsheet | Done | 1,3 | 2013-04-27 | 2013-04-27 | 1 - Invoke from menu item 2 - view on top of spreadsheet |  | https://developers.google.com/apps-script/uiapp#DisplayingSpreadsheet